## Slide 1: Society of American Gastrointestinal and Endoscopic Surgeons (SAGES)
April 2018
Welcome to YM Learning
YM Education PMO

## Slide 2
Today’s Agenda
Team introductions
What got you excited about YML-CW?
Goals / Contract SOW review
Growth Opportunities
Project Timeline Phases
Kickoff Date

## Slide 3
SAGES - Welcome to the Family!
Jeff DeSimone
Sr. Project Manager, LMS
Jeff.desimone@communitybrands.com
Reni Bankole
Head of PMO, Dir of Implementation
reni.bankole@communitybrands.com
Vanessa Pryor - SAGES
IT Manager
vanessap@sages.org
Chris Hills
Sr. Business Analyst, LMS
Chris.hills@communitybrands.com
Jen Koher
Business Analyst, LMS
Jen.koher@communitybrands.com
Jason Levine - SAGES
CTO
Linda Schultz - SAGES
Manager of Masters Program

## Slide 4
What got you excited about YML-CW?

## Slide 5
Contract SOW review
Discovery – review strategy, document requirements and plan implementation timing
Branding & Configuration – choose from standard template
Configuration of Features & Widgets – Dashboard widgets
Course Migrations – 3 educational activities – courses?
Advanced Module/Custom – MOC, Institutions, Self assessment, Warm Seat
Integrations – Simple SSO, Shopping Cart, Course completion info push back to CRM, GoToWebinar platform, Webassessor, DecisionSim
Reporting – ABS
Custom domain name
Training – Virtual Webinars, Content creation training, Portal Training
Customizations – Exams: FES & FLS exams setup
Grades /Transcript Migration – Holding Tank for ~60k records

## Slide 6
Growth Opportunities for SAGES ??
Growth Opportunities

## Slide 7
LMS Implementation Project Phases
Kick-off
Requirements
Implementation
Deploy
Transition
Onsite Kickoff Project Scope clarified
Project Plan Defined
Work streams defined and documented
Statement of Work approved
Work streams
executed
QA
Production Readiness
Go – live
Transition to support

## Slide 8
LMS Implementation Timeline – Just an estimate subject to change
2018
2018
Apr
May
Jun
Jul
Aug
Project Kickoff
4/18/18
Requirements Analysis/ Specifications Completed
5/17/2018
SOW Approval - SAGES
6/13/2018
Content Readiness
7/5/18
Staging Development Completed
7/20/18
SAGES Completes
UAT
8/3/18
Staging Approval
7/2/18
Production Approval - SAGES
8/30/2018
Portal Completed -Soft Launch
8/27/18
Transition To Support
9/12/2018

## Slide 9
Next steps: Pre Kick-Off Discovery Mtg
YML Implementation Team
Prepare for the onsite kick-off
SAGES Team
Get ready to start implementation!
Next step
Pre Kick-off Discovery Mtg is scheduled for:

## Slide 10: Q & A
Thank you!