## Sheet1
Task Name | % Work Complete | Duration | Start | Finish | Resource Names
LMS Implementation Project | 8% | 169 days | Wed 12/21/16 | Tue 8/22/17
Kickoff | 77% | 9 days | Wed 12/21/16 | Tue 1/10/17
Contract Executed | 100% | 1 day | Wed 12/21/16 | Wed 12/21/16 | CLIENT NAME,Tamer Ali
Milestone 1 - 35% | 100% | 0 days | Wed 12/21/16 | Wed 12/21/16
Prepare Kickoff Deliverables | 75% | 7 days | Tue 12/27/16 | Tue 1/10/17 | Jeff Desimone,Michele Windsor,Reni Bankole,Rob Luck
Project Kickoff - Onsite Meeting | 100% | 2 days | Mon 1/9/17 | Tue 1/10/17
Client Onboarding - Access to Default Site, Access to Project Repository (Client Name folder on Box) | 100% | 1 day | Tue 1/10/17 | Tue 1/10/17 | Michele Windsor
Kickoff Complete - Introduction and Onsite Meeting, Client Onboarding | 100% | 0 days | Tue 1/10/17 | Tue 1/10/17
Requirements Gathering - Detailed Specifications | 4% | 61 days | Wed 1/11/17 | Wed 4/5/17
Develop Integrated Project Plan | 100% | 2 days | Wed 1/11/17 | Thu 1/12/17 | Reni Bankole,Michele Windsor
Client Name Review, Update, and Approval of Integrated Project Plan | 50% | 3 days | Mon 1/16/17 | Wed 1/18/17 | CLIENT NAME
Administration Readiness | 100% | 6 days | Tue 1/17/17 | Tue 1/24/17
Admin Training - Session 1 | 100% | 1 day | Tue 1/17/17 | Tue 1/17/17 | Steve German
Admin Training - Session 2 | 100% | 1 day | Tue 1/24/17 | Tue 1/24/17 | Steve German
Integration | 0% | 17 days | Wed 1/25/17 | Thu 2/16/17
Desired User Experience Definition - ACR & Client Name UX - Business Rules, CE, Certification | 0% | 5 days | Wed 1/25/17 | Tue 1/31/17
Integration and Data Exchange Specifications Submitted | 0% | 3 days | Wed 2/1/17 | Fri 2/3/17 | Jeff Desimone
Integration Follow-up Discussion - API Calls | 0% | 2 days | Mon 2/6/17 | Tue 2/7/17 | Jeff Desimone,Michele Windsor,CLIENT NAME,Chris Hills
Integration Specifications Updated | 0% | 2 days | Wed 2/8/17 | Thu 2/9/17 | Chris Hills,Michele Windsor
Integration & Data Exchange Specifications Approved | 0% | 5 days | Fri 2/10/17 | Thu 2/16/17 | CLIENT NAME
Platform Configuration - Selection of Features and Modules | 0% | 19 days | Wed 1/25/17 | Mon 2/20/17
Configuration follow-up discussion | 0% | 2 days | Wed 1/25/17 | Thu 1/26/17 | CLIENT NAME,YM
Dashboard Widgets Defined | 0% | 5 days | Fri 1/27/17 | Thu 2/2/17 | CLIENT NAME,YM
Tabs and Tab Named Defined | 0% | 3 days | Fri 2/3/17 | Tue 2/7/17 | CLIENT NAME,YM
Configuration Settings Defined (Timezone, Credit types) | 0% | 2 days | Wed 2/8/17 | Thu 2/9/17 | CLIENT NAME
Configuration Specifications Submitted | 0% | 2 days | Fri 2/10/17 | Mon 2/13/17 | YM
Configuration Specifications Approved | 0% | 5 days | Tue 2/14/17 | Mon 2/20/17 | CLIENT NAME
Content (Assessments, Evaluations and Courses) | 0% | 41 days | Wed 1/18/17 | Wed 3/15/17
Client Name Sends First Set of Content - Physical Files to YM to review for Instructional Design ideas | 0% | 3 days | Wed 1/18/17 | Fri 1/20/17 | CLIENT NAME
Content Follow-up Discussion | 0% | 1 day | Mon 2/27/17 | Mon 2/27/17 | CLIENT NAME,YM
Content Story boards defined | 0% | 5 days | Tue 2/28/17 | Mon 3/6/17 | Louise Platiel,Nayela Hoda
Content Specifications Submitted | 0% | 2 days | Tue 3/7/17 | Wed 3/8/17 | Jeff Desimone,Nayela Hoda
Content Specifications Approved | 0% | 5 days | Thu 3/9/17 | Wed 3/15/17 | CLIENT NAME
Branding (Look & Feel) | 0% | 15 days | Wed 1/25/17 | Tue 2/14/17
Sample dashboards submitted | 0% | 1 day | Wed 1/25/17 | Wed 1/25/17 | Jeff Desimone
Branding guidelines submitted by Client Name | 0% | 3 days | Thu 1/26/17 | Mon 1/30/17 | CLIENT NAME
Branding follow-up Discussion | 0% | 1 day | Tue 1/31/17 | Tue 1/31/17 | CLIENT NAME,YM
Branding Specifications (Mock-ups) Submitted | 0% | 3 days | Wed 2/1/17 | Fri 2/3/17 | Jeff Desimone
Branding Specifications (Mock-ups) Refined | 0% | 2 days | Mon 2/6/17 | Tue 2/7/17 | YM,Jeff Desimone
Branding Specifications (Mock-ups) Approved | 0% | 5 days | Wed 2/8/17 | Tue 2/14/17 | CLIENT NAME
Customizations | 0% | 13 days | Tue 3/7/17 | Thu 3/23/17
Customizations Defined | 0% | 5 days | Tue 3/7/17 | Mon 3/13/17 | CLIENT NAME,YM
Customization Follow - up Call | 0% | 1 day | Tue 3/14/17 | Tue 3/14/17 | CLIENT NAME,YM
Customization Solution Specifications Compiled & Submitted | 0% | 2 days | Wed 3/15/17 | Thu 3/16/17 | Michele Windsor,Reni Bankole
Customizations Solution Specifications Approved | 0% | 5 days | Fri 3/17/17 | Thu 3/23/17 | CLIENT NAME
LMS Requirements Specifications Completed | 0% | 0 days | Thu 3/23/17 | Thu 3/23/17 | Jeff Desimone,Michele Windsor
Statement of Work | 0% | 9 days | Fri 3/24/17 | Wed 4/5/17
LMS Implementation Statemement of Work (SOW) Created and Released | 0% | 4 days | Fri 3/24/17 | Wed 3/29/17 | Jeff Desimone,Michele Windsor
SOW Signed and Approved | 0% | 5 days | Thu 3/30/17 | Wed 4/5/17 | CLIENT NAME
Implementation Project Plan Updated by YM | 0% | 2 days | Thu 3/30/17 | Fri 3/31/17 | Reni Bankole
Requirements Phase Completed - SOW Executed | 0% | 0 days | Wed 4/5/17 | Wed 4/5/17
Implementation - Requirements Execution | 0% | 35 days | Thu 3/9/17 | Wed 4/26/17
Staging Environment Readiness | 0% | 1 day | Thu 4/6/17 | Thu 4/6/17
Create Staging Site/Confirm Team Access to Site | 0% | 1 day | Thu 4/6/17 | Thu 4/6/17 | Jeff Desimone,Michele Windsor,Chris Hills
Integration | 0% | 13 days | Thu 4/6/17 | Mon 4/24/17
Desired User Experience - ACR & Client Name UX | 0% | 2 days | Thu 4/6/17 | Fri 4/7/17 | YM
Integration and Data Exchange | 0% | 2 days | Mon 4/10/17 | Tue 4/11/17 | YM
Integration Review | 0% | 4 days | Wed 4/12/17 | Mon 4/17/17 | CLIENT NAME
Integration Updated | 0% | 2 days | Tue 4/18/17 | Wed 4/19/17 | YM
Integration & Data Exchange Approved | 0% | 3 days | Thu 4/20/17 | Mon 4/24/17 | CLIENT NAME
Platform Configuration - Development of Features and Modules | 0% | 15 days | Thu 4/6/17 | Wed 4/26/17
Configuration | 0% | 2 days | Thu 4/6/17 | Fri 4/7/17 | Chris Hills
Dashboard Widgets | 0% | 2 days | Mon 4/10/17 | Tue 4/11/17 | Chris Hills
Page & Navigation (tabs) Layout | 0% | 2 days | Wed 4/12/17 | Thu 4/13/17 | Chris Hills
Configuration Settings (Timezone, Credit types, User Groups) | 0% | 2 days | Fri 4/14/17 | Mon 4/17/17 | Chris Hills
Configuration Review | 0% | 2 days | Tue 4/18/17 | Wed 4/19/17 | CLIENT NAME,YM
Configuration Approved | 0% | 5 days | Thu 4/20/17 | Wed 4/26/17 | CLIENT NAME
Content (Assessments, Evaluations and Courses) | 0% | 18 days | Thu 3/9/17 | Mon 4/3/17
Content | 0% | 5 days | Thu 3/9/17 | Wed 3/15/17 | Louise Platiel,Nayela Hoda
Content Story boards | 0% | 5 days | Thu 3/16/17 | Wed 3/22/17 | Louise Platiel,Nayela Hoda
Content Review | 0% | 3 days | Thu 3/23/17 | Mon 3/27/17 | YM
Content Approved | 0% | 5 days | Tue 3/28/17 | Mon 4/3/17 | CLIENT NAME
Branding (Look & Feel) | 0% | 11 days | Thu 4/6/17 | Thu 4/20/17
Dashboards | 0% | 2 days | Thu 4/6/17 | Fri 4/7/17 | Chris Hills
Branding Specifications Developed | 0% | 2 days | Mon 4/10/17 | Tue 4/11/17 | Chris Hills
Branding Specifications Refined | 0% | 2 days | Wed 4/12/17 | Thu 4/13/17 | Chris Hills
Branding Approved | 0% | 5 days | Fri 4/14/17 | Thu 4/20/17 | CLIENT NAME
Customizations | 0% | 9 days | Fri 3/24/17 | Wed 4/5/17 | Jeff Desimone,Michele Windsor
Customizations Specifications Accepted and Approved for Development | 0% | 1 day | Fri 3/24/17 | Fri 3/24/17 | John Sun
Customizations Solution Developed | 0% | 3 days | Mon 3/27/17 | Wed 3/29/17 | YM Development Team
Customizations Approved | 0% | 5 days | Thu 3/30/17 | Wed 4/5/17 | CLIENT NAME
Staging QA - Internal | 0% | 2 days | Thu 4/6/17 | Fri 4/7/17 | QA Analyst
User Acceptance Testing (UAT) - Staging Approval: Testing and Approval by Client Name | 0% | 10 days | Mon 4/10/17 | Fri 4/21/17 | CLIENT NAME
Product Adjustment after Client Feedback | 0% | 2 days | Mon 4/24/17 | Tue 4/25/17 | Jeff Desimone
Staging Development Complete | 0% | 0 days | Tue 4/25/17 | Tue 4/25/17
Milestone Payment - 15% | 0% | 0 days | Tue 4/25/17 | Tue 4/25/17
Deploy - Production | 0% | 70 days | Mon 4/10/17 | Fri 7/14/17
Release Planning | 0% | 5 days | Mon 4/10/17 | Fri 4/14/17
Release Plan Development | 0% | 2 days | Mon 4/10/17 | Tue 4/11/17 | Rob Luck,Jeff Desimone,Michele Windsor
Release Plan Approval | 0% | 3 days | Wed 4/12/17 | Fri 4/14/17 | CLIENT NAME
Pre-Production | 0% | 3 days | Wed 4/26/17 | Fri 4/28/17 | Jeff Desimone
Configuration and Branding Updated | 0% | 1 day | Wed 4/26/17 | Wed 4/26/17 | Jeff Desimone
Integration Updated and Tested | 0% | 1 day | Thu 4/27/17 | Thu 4/27/17 | Jeff Desimone
Sample Content Migrated from Staging | 0% | 1 day | Fri 4/28/17 | Fri 4/28/17 | Jeff Desimone
Pre-Production Complete | 0% | 0 days | Fri 4/28/17 | Fri 4/28/17
Production Readiness - "Live" Site | 0% | 24 days | Mon 5/1/17 | Thu 6/1/17
Production Created | 0% | 1 day | Mon 5/1/17 | Mon 5/1/17 | Jeff Desimone
Production QA - Internal | 0% | 3 days | Tue 5/2/17 | Thu 5/4/17 | QA Analyst
Data Migration | 0% | 20 days | Fri 5/5/17 | Thu 6/1/17
Migrate Client-Approved Content from Staging to Production | 0% | 2 days | Fri 5/5/17 | Mon 5/8/17 | Latif Pothiawala,Nayela Hoda
Review Content: User Flows, Grading, etc | 0% | 3 days | Tue 5/9/17 | Thu 5/11/17 | Latif Pothiawala,Nayela Hoda
Content Revisions Rounds (as needed / if needed) | 0% | 3 days | Mon 5/15/17 | Wed 5/17/17 | Latif Pothiawala,Louise Platiel,Nayela Hoda
Production QA - Review Integration, Branding and Configuration, Customizations, User Records | 0% | 6 days | Thu 5/18/17 | Thu 5/25/17 | QA Analyst
LMS Production Review and Approval | 0% | 5 days | Fri 5/26/17 | Thu 6/1/17 | CLIENT NAME
Milestone Payment - 50% | 0% | 0 days | Thu 6/1/17 | Thu 6/1/17
Production Complete | 0% | 0 days | Thu 6/1/17 | Thu 6/1/17
YM Check-in: 10 Days after Production Release | 0% | 1 day | Mon 6/12/17 | Mon 6/12/17 | Jeff Desimone
YM Check-in: 30 Days after Production Release | 0% | 1 day | Fri 7/14/17 | Fri 7/14/17 | Michele Windsor
Transition to Support | 0% | 37 days | Wed 6/28/17 | Thu 8/17/17
Develop Transition Document - Update Transition to Support Template | 0% | 4 days | Wed 6/28/17 | Mon 7/3/17 | Jeff Desimone
Client Go-Live (Soft Launch) | 0% | 1 day | Wed 7/5/17 | Wed 7/5/17 | Jeff Desimone,Michele Windsor
Introduction to Live-Site Support: 10 Days after Client Go-Live | 0% | 1 day | Thu 7/20/17 | Thu 7/20/17 | Jeff Desimone,Michele Windsor,Tamer Ali
Conduct Transition to Support Meeting | 0% | 1 day | Thu 7/6/17 | Thu 7/6/17 | Jeff Desimone,Michele Windsor,Jessica Yasin,CLIENT NAME
YM Check-in: 30 Days after Client Go-Live | 0% | 1 day | Thu 8/17/17 | Thu 8/17/17 | Michele Windsor
Transition to Support Complete | 0% | 0 days | Thu 8/17/17 | Thu 8/17/17
Project Close | 0% | 3 days | Fri 8/18/17 | Tue 8/22/17
Administrative - Close Project Financials in Salesforce | 0% | 1 day | Fri 8/18/17 | Fri 8/18/17 | Michele Windsor
Administrative - Close Project in Intervals | 0% | 1 day | Fri 8/18/17 | Fri 8/18/17 | Jeff Desimone
Conduct Lessons Learned Meeting | 0% | 1 day | Mon 8/21/17 | Mon 8/21/17 | Jeff Desimone
Update Lessons Learned Knowledge Base | 0% | 2 days | Mon 8/21/17 | Tue 8/22/17 | Jeff Desimone
Project Closed | 0% | 0 days | Tue 8/22/17 | Tue 8/22/17