## Cover Page
LMS Implementation RACI Matrix
Purpose: | A RACI matrix is a responsibility assignment marix that is used for resource allocation and shows who is Responsible, Accountable, must be Consulted with, and must stay Informed on a project
Project Identification
Client Name: | SAGES LMS Implementation RACI Matrix
Project Name: | LMS Implementation | Project Manager: | Jeff DeSimone | Current Phase:
Project Start Date: | 2018-04-06 | Project End Date: |  | Last Update Date: | 4/2/2018

## Data Validation (hidden)
Kickoff
Requirements
Implementation
Deploy
Transition

## LMS Implementation RACI
SAGES LMS Implementation Project RACI Matrix
|  | Responsible, Accountable, Consulted, Informed | [10 empty] | Transition to Support
Phase | Deliverables | PM | PMO | SAGES | Exec. Sponsor | Training | Business Analyst | Sales | Dev | Content Team | QA Analyst | Support
Kickoff | YM Client Welcome Call | R | R, A |  | C |  |  | C
| Prepare Kickoff Assets | A | R |  | I |  |  | C
| Conduct Kickoff Call | R | A |  | I
| Client on-boarding - Access to default system, login to box shared drive, send requirements workshop email | R | A | I | I
Requirements | Client Admin Training Sessions 1 - 4 | A | I | R | I | R
| Client provides Configuration, Integration, Branding, Content, Specifications | A | I | R | [5 empty] | C
| SOW Development | R | I | I | A |  |  | C
| SOW Approval - Meeting and Sign-off | A | A | R | I
| Implementation Project Plan development and release | R | A | I | C |  | C |  | C
| Project plan approval | A | I | R | I
Implementation | Sprint Planning | A | R | I |  |  |  |  | I
| Create Staging Environment | A | [6 empty] | R
| Client Admin Training 2 | A | I | R |  | R
| Develop Branding | A | [6 empty] | R
| Develop Configuration | A | [6 empty] | R
| Develop Integration | A | [6 empty] | R
| Develop Content | A | [7 empty] | R
| Branding, Configuration, Integration Approval | A |  | R
| Content Approval | A |  | R | [5 empty] | C
| Loading of Content | A | [6 empty] | C | R
| Branding, Configuration, Integration, QA | A |  |  |  |  | R
| Content QA | A | [7 empty] | R | R
Creation of Production Environment
| Content and Taxonomy Approval - Ready for Production, Add-ons like HT, Institutions, | A |  | R
| Client Admin Training 3 | A |  |  |  |  | R
| Staging Review and Approval | A |  | R
Deploy | Release Planning | A | R | C |  |  |  |  | I | I
| Release Plan Approval | A | I | R
| Pre-Production Environment Development | A | [6 empty] | I/R
| Production Environment Development | A | [6 empty] | R
| Content Migration from Staging to Production | A | [7 empty] | R
| Review Content , User Flows, Branding, Grading, Configuration, Integration | A | [8 empty] | R
| Client Approval of Production | A |  | R
| Education Portal Production Readiness Notification | A/R | I | I | I
Transition to Support | Transition to Support Planning | A/R | [9 empty] | C
| Transition to Support Workshop/Meeting | A/R |  | C, I | C | [6 empty] | I
| 10 Days Post- Implementation Check-in | A/R |  | C, I
| 30 Days Post- Implementation Check-in |  |  | C, I | A/R
Project Closing | Administrative Closure - Schedule | R | A |  | I
| Administrative Closure - Project Financials |  |  |  | A/R
| Update Lessons Learned Document | R |  |  | C |  | C | C | C | C | C | C

## Definition
Description of Terms
A RACI chart showcases three elements of roles and responsibilities:
a) Role Conception: what people think their jobs are
b) Role Expectation: what others in the organizatiion think another person's job function is and how it should be carried out
Role Behavior: what team members actually do to contribute to a successful project
R = Responsible: the role owning the Action / Task, does the work
A = Accountable: the role to whom "R" is accountable and has approval authority. Only one person can be accountable for a task. This person makes decisions regarding the task.
C = Consulted: the role providing information and/or expertise necessary to complete the deliverable
I = Informed: the role requiring notification of results, decisions and actions on the tasks but need not necessarily be consulted